## Timetable
PROGRAM TITLE | LAST CHANCE TO BOOK EVENT (1 year to 38 weeks) | PLANNING MEETING & PRICING | EVENT ONLINE + MARK YOUR CALENDER E-BLAST | PROGRAMMING CONFRIMED (Brochure to graphics) + OPEN REGISRATION | MAIL BROCHURE + E-BLAST + ARTICLE REMINDER + SPEAKER/COUNCIL HOTEL RESERVATIONS | E-BLAST SPEAKER RESERVATION + ARTICLE DEADLINE REMINDER | HOTEL RESERVATION + ARTICLE SUBMISSION DEADLINE | E-BLAST FINAL ARTICLE + CONFIRM A/V REQUIREMENTs | 1 week out | DATE OF PROGRAMMING
Weeks from Program | 38 | 28 | 21 | 16 | 12 | 6 | 5 | 3 | 1 | 0
Course Title | 2012-12-27 | 2013-03-28 | 2013-05-16 | 2013-06-20 | 2013-07-18 | 2010-11-22 | 2013-09-05 | 2013-09-19 | 2013-10-03 | 2013-10-10
Course Title | 2010-05-10 | 2010-08-09 | 2010-09-27 | 2010-11-01 | 2010-11-29 | 2011-01-10 | 2011-01-17 | 2011-01-31 | 2011-02-14 | 2011-02-21
Course Title | 2010-06-07 | 2010-09-06 | 2010-10-25 | 2010-11-29 | 2010-12-27 | 2011-02-07 | 2011-02-14 | 2011-02-28 | 2011-03-14 | 2011-03-21
Course Title | 2010-06-28 | 2010-09-27 | 2010-11-15 | 2010-12-20 | 2011-01-17 | 2011-02-28 | 2011-03-07 | 2011-03-21 | 2011-04-04 | 2011-04-11
Sample with formulas | 2010-07-19 | 2010-09-27 | 2010-11-15 | 2010-12-20 | 2011-01-17 | 2011-02-28 | 2011-03-07 | 2011-03-21 | 2011-04-04 | 2011-04-11

## Task Description
TIMETABLE - DESCRIPTION OF TASKS (1/5/11)
Note regarding marketing lists: when creating marketing lists, make sure you eliminate registrants of the course you are marketing on each list created (so that we don't continue marketing to someone who is already registered.
38 weeks | Biz Meeting | Planners to meet with Cyd/Pam to discuss the overview of last year's course. What went well, what didn’t, do we need to adjust marketing plan, and budget discussion.
34 weeks | Initial Contact | Initial Contact with Course/Insitute Director Invite person to be course director and coordinate a date for the planning meeting
28 weeks | Planning Meeting | Planning meeting should be held on or around this date. Ask Course Director for list of invitees and send out invitation at least 4 weeks in advance.
25 weeks | Pricing Meeting | Planners to meet with Cyd/Pam regarding the pricing/reg fees for the course. Prior to meeting, planners to fill out pricing worksheet with information from last year's course and for current year's course. Then, forward to facilities for them to fill in facility information such as food/beverage, parking, internet, electrical connections, hotel rate and cutoff date.
23 weeks | Confirm Program + Preview Page Online + Eblast + Author Packets | All speakers (or most speakers) should be confirmed by this date. Create the preview page and coordinate with David regarding layout. Turn on registration and get the preview page put up online. Do an eblast with a link to the preview page Send out author/speaker packets.
21 weeks | Brochure to Marketing Team | Create copy for brochure and email it with a print project form to David and Joan. They will put it in In Copy and let you know when the brochure is ready for proofing/editing.
16 weeks | Course Director Letter via Eblast (+ possibly hard copy) | Create a course director letter (the course director can draft the letter or you can draft it and run by CD for approval). Ask for CD picture and signature to include in the eblast. Send photo and signature to David so he can add them to the artwork area of the eblast tool. Send the CD Eblast to your eblast mailing list. A hard copy of the CD letter may also be sent - this will be determined at the Biz Mtg. If you decide to send a hard copy in addition to the eblast - the hard copy will only get sent to prior registrants from the last 3 years - FIRST CLASS. Also, if you send a hard copy in addition to the eblast, make sure your marketing list for the eblast excludes the 3 years prior reg.
14 weeks | Brochure to Printing Division | At least one week prior to this date, send the printing coordinator (Tami Knoll) the particulars for your brochure (flat/folded, number of pages, full color, quantity to be printed). She will send this information out to vendors for a quote so when you send the brochure to her - that step will already be taken care of. Create a workorder to email to Tami along with your first class mailing list and your first bulk mailing list. The marketing team will send Tami the correct files for the printer.
12 weeks | First Class Mailing of Brochure (send to prior reg only) + 1st Bulk Mailing of Brochure to Wide Marketing List + Eblast to eblast list + 1st Article Reminder Notice | Send First Class brochure to prior registrants of this course only (3 years prior reg) Send 1st bulk brochure mailing to a wide marketing group consisting of the following (keeping in mind the target number of mailings) of : - prior reg of similar courses - interest area/s (be selective - adding random interest areas can increase your #'s drastically with little return) - section members of section/s related to this area of practice - board certified attorneys related to this area of practice - possibly State Bar College members Send 1st article reminder notice to authors speakers. Send them a few brochures and a letter that highlights upcoming deadlines.
10 weeks | 2nd Brochure Mailing to Narrow Marketing List | Regenerate your 2nd brochure mailing list and email it to Tami at least one week prior to this date. Send 2nd bulk brochure mailing to a narrow group such as: - prior registrants of same courses - prior registrants of similar courses - possible section/tbls members (keep in mind the target number of mailings)
8 weeks | 3rd Brochure Mailing to Narrow Marketing List + Eblast (emphasis on hotel cutoff) + 2nd Article Reminder Notice | Regenerate your 3rd brochure mailing list and email it to Tami at least one week prior to this date. Send 3rd bulk brochure mailing to a narrow group such as: - same list as 2nd mailing or . . . - prior registrants only (keep in mind the target number of mailings) Send Eblast out to eblast marketing list and emphasize the hotel cutoff date) Send out 2nd Article Reminder notice to authors/speakers that their articles are due in 2 weeks
6 weeks | Eblast (emphasis on hotel cutoff and early reg cutoff) + Article Deadline | This can be a little bit of a "floating" date depending on the actual hotel cutoff date (meaning you may send this eblast out 5 weeks prior to the course or 6 weeks prior to the course). Check with facilities on the actual hotel cutoff date and Send the eblast 1-2 weeks prior to the actual hotel cutoff date. Use the cutoff date in the subject line of this eblast. Article deadline is this day. Late author notices need to go out this week.
5 weeks | Speaker Reservation Reminder | Send a reminder to speakers to make their travel arrangements (if needed). This is also a good time to nudge those again with late articles.
3 weeks | Eblast (emphasis on early reg deadline) + A/V Request | On the Monday of the week of the early registration cutoff, send eblast out to your eblast marketing list and emphasize the early registration cutoff. Use the cutoff date in the subject line of the eblast. Send out audio/visual requests to speakers and let them know when you need their list of equipment needs and their ppt.
1 week | Eblast Registrants | Eblast registrants of the course with details about location and link to location website, parking and parking locations link if unique to facility, starting time of the course and a link to the course brochure, and any other details you would like to highlight. Subject line of eblast can be something like: "See You Thursday at the Fiduciary Litigation Trial Notebook Course in Austin"
1 week after live course | Thank You Letters + Staff Evaluation | Send out thank you letters to the course director and to all course faculty. Fill out your staff evaluation of the course.
3 weeks prior to video replays | Eblast | Send out an eblast about the video replays and send to your eblast marketing list with these changes - make sure those in the list "also match bar districts in the geographic area of the video replay" - make sure those in the list "also match the birthday month/s that the video is being replayed".